## Worksheet
Task | Owner | Due Date | Status | Progress (%) | Priority | Resources Required | Dependencies | Meeting Notes
Define team goals for Q3 | Sarah Johnson | 2023-08-15 | In Progress | 60% | High | Project Manager, Marketing Lead | None | Align with strategic objectives; draft KPIs.
Schedule bi-weekly team syncs | Michael Chen | <>2023-08-10Completed | 100% | Medium | Calendar, Zoom access | Team goal definition | Confirmed meeting times; shared with all members.
Develop collaboration workflow document | Lisa Rodriguez | 2023-09-01 | Not Started | 0% | High | Team members, HR support | Goal definition complete | Draft to be reviewed by leadership.
Conduct team feedback survey | David Kim | 2023-08-25 | In Progress | 40% | Medium | Survey tool, team emails | Sync meetings completed | Pilot survey distributed to 50% of team.
Organize Q3 project kick-off meeting | Emma Turner | 2023-08-28 | Scheduled | 0% | High | All project leads, stakeholders | Workflow document ready | Agenda to be finalized by August 25.