## Worksheet
Task | Team Member | Assigned Date | Due Date | Status | Progress (%) | Notes
Project Planning Meeting | Alex Rivera | 2024-04-05 | 2024-04-10 | In Progress | 65% | Outline scope, define deliverables, assign roles.
Design Phase | Samira Khan | 2024-04-08 | 2024-04-15 | Not Started | 0% | Create wireframes and UI mockups.
Development Sprint | Jordan Lee | 2024-04-12 | 2024-04-25 | In Progress | 40% | Frontend implementation in progress.
Client Review Session | All Team | 2024-04-20 | 2024-04-23 | Scheduled | 0% | Final feedback and approval needed.
Final Testing & Deployment | Lena Torres | 2024-04-25 | 2024-05-01 | Not Started | 0% | QA testing and go-live preparation.