## Worksheet
Week | Team Objective | Assigned Roles | Key Deliverables | Deadlines | Progress Status | Team Notes
Week 1 | Define project scope and goals | Project Manager, Product Owner | Scope document, stakeholder alignment report | Monday, April 8 | Completed | All stakeholders confirmed.
Week 2 | Design team workflow and collaboration process | UX Designer, Dev Lead | Workflow diagram, meeting agenda template | Friday, April 12 | In Progress | Reviewing feedback from initial team sessions.
Week 3 | Develop sprint planning framework | Scrum Master, QA Lead | Sprint planning checklist, backlog prioritization matrix | Thursday, April 25 | Planned | Finalizing team capacity estimates.
Week 4 | Conduct first sprint kickoff meeting | All Team Members | Sprint goals, team cadence agreement | Monday, May 6 | Scheduled | Preparation materials in progress.
Week 5 | Review sprint performance and adjust plan | Project Manager, Team Leads | Sprint retrospective report, updated roadmap | Friday, May 10 | Planned | Feedback from sprint 1 will be analyzed.