## Worksheet
Category | Team Member | Assigned Task | Due Date | Status | Progress (%)
Project Planning | Alex Johnson | Define team roles and responsibilities | 2024-03-15 | Completed | 100%
Design Phase | Samantha Lee | Create wireframes and UI mockups | 2024-03-25 | In Progress | 75%
Development | Marcus Wong | Build backend APIs and database schema | 2024-04-10 | Not Started | 0%
Testing | Taylor Reed | Conduct unit and integration tests | 2024-04-20 | Scheduled | 0%
Deployment | Jordan Patel | Deploy to staging and monitor performance | 2024-05-01 | Not Started | 0%