## Worksheet
Date | Task | Assigned To | Status | Priority | Estimated Time (min) | Actual Time (min) | Progress (%) | Notes
2024-04-05 | Project Kickoff Meeting | Alex Johnson | Completed | High | 60 | 55 | 100% | All team members confirmed. Agenda finalized.
2024-04-06 | Requirement Gathering | Sara Lee | In Progress | High | 90 | 45 | 50% | Client feedback collected. Final review scheduled for tomorrow.
2024-04-07 | Design Mockups Review | Marcus Wong | Pending | Medium | 120 | 0 | 0% | Waiting on client approval. Will send draft by end of day.
2024-04-08 | Weekly Standup Meeting | Team Lead | Completed | Low | 30 | 25 | 83% | All team members updated on progress and blockers.