## Worksheet
Date | Task | Assignee | Status | Priority | Estimated Time (hrs) | Actual Time (hrs) | Notes
2023-10-05 | Finalize project scope document | John Doe | Completed | High | 8 | 7.5 | Document reviewed and approved by stakeholders.
2023-10-06 | Schedule team stand-up meeting | Jane Smith | In Progress | Medium | 2 | 1.5 | Meeting scheduled for 10:00 AM, to be recorded.
2023-10-07 | Review budget proposal | Mike Johnson | Pending | High | 6 | 0 | Waiting for finance team input.
2023-10-08 | Draft presentation slides | Sarah Lee | Completed | 4 | 4 | Slides shared with marketing team for feedback.