## Worksheet
Date | Team Member | Task Assigned | Status | Deadline | Progress (%) | Notes
2024-04-01 | Sarah Johnson | Project Kickoff Meeting Planning | Completed | 2024-03-31 | 100% | All meeting materials shared via Teams.
2024-04-05 | David Chen | Wireframe Design Review | In Progress | 2024-04-10 | 65% | Feedback from UX team pending.
2024-04-08 | Maria Lopez | Develop Backend API Endpoints | Pending | 2024-04-15 | 0% | Waiting for database schema approval.
2024-04-10 | James Williams | User Testing Session Setup | Scheduled | 2024-04-18 | 0% | Participants confirmed. Materials in draft.
2024-04-15 | Aisha Patel | Final Report Drafting | Not Started | 2024-04-25 | 0% | Waiting for stakeholder input.