## Worksheet
Date | Team Member | Task Description | Assigned To | Priority Level | Estimated Time (hrs) | Status | Progress (%) | Meeting Notes | Deadline
2024-04-01 | Alice Johnson | Finalize project scope document | Alice Johnson | High | 8 | In Progress | 60% | Discussed with stakeholders; feedback received on section 3. | 2024-04-10
2024-04-03 | Mark Davis | Conduct team sprint planning session | Mark Davis | Medium | 4 | Scheduled | 0% |  | 2024-04-05
2024-04-05 | Sophia Lee | Review design mockups with UX team | Sophia Lee | High | 6 | Pending Approval | 30% | Feedback required on navigation flow. | 2024-04-15
2024-04-10 | James Wilson | Prepare Q3 goals presentation | James Wilson | Medium | 10 | Not Started | 0% |  | 2024-05-01
2024-04-15 | Elena Martinez | Coordinate cross-departmental sync meeting | Elena Martinez | Medium | 3 | Completed | 100% | All departments aligned on deliverables. | 2024-04-15