## Worksheet
Date | Team Member | Task | Assigned To | Status | Deadline | Notes / Comments
2024-04-01 | Alex Johnson | Project Kickoff Meeting | All Team Members | Completed | 2024-04-01
2024-04-03 | Mia Chen | Design Wireframes | UI Team | In Progress | 2024-04-10 | Need feedback from product lead by 4/8.
2024-04-05 | Jordan Lee | Develop Backend API | Engineering Team | Not Started | 2024-04-15 | Sync with frontend team on data structure.
2024-04-07 | Taylor Reed | Team Retrospective | All Team Members | Completed | 2024-04-07 | Action items logged in Jira.
2024-04-10 | Sam Patel | User Testing Session | QA Team | Scheduled | 2024-04-12 | Participants: 5 users, remote setup.