## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Meeting Notes | Risk Assessment
Define Project Scope | Anna Lopez | 2024-03-01 | 2024-03-15 | In Progress | High |  | Align with stakeholders; finalize deliverables. | Low - Scope change risk
Develop Project Timeline | James Chen | 2024-03-16 | 2024-03-31 | Not Started | Medium | Define Scope Task | Estimate resource allocation. | Medium - Resource availability
Team Kickoff Meeting | Sarah Kim | 2024-03-05 | 2024-03-05 | Completed | High |  | Set team goals, assign roles, review tools. | None
Design Collaboration Workflow | Liam Reed | 2024-04-01 | 2024-04-15 | Not Started | High | Timeline Task, Scope Task | Standardize communication channels and approval steps. | Medium - Tool compatibility issues
Weekly Team Syncs (Ongoing) | Team Leads | 2024-03-06 | Ongoing | On Track | Medium |  | Review progress, resolve blockers. | Low - Minor delays in updates