## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies | Notes
Project Kickoff Meeting | John Smith | 2024-04-01 | Completed | High | - | Finalize project vision and objectives.
Team Onboarding | Sarah Lee | 2024-04-10 | In Progress | Medium | Kickoff Meeting completed | Distribute role descriptions and access rights.
Requirements Gathering | Michael Chen | 2024-04-25 | Pending | High | Team Onboarding completed | Workshops with stakeholders to define needs.
Design Phase Planning | Lisa Wong | 2024-05-10 | Not Started | Medium | Requirements finalized | Create wireframes and user flow diagrams.
Prototype Review Session | Team Collaboration Hub | 2024-05-25 | Pending | High | Design Phase Planning completed | Feedback from stakeholders to be collected.