## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Notes
Project Kickoff Meeting | Sarah Johnson | 2024-03-15 | 2024-03-15 | Completed | High | Finalize project scope and objectives with stakeholders.
Requirements Gathering | David Kim | 2024-03-16 | 2024-04-10 | In Progress | High | Engage key users to document functional and non-functional requirements.
Design Phase (UI/UX) | Lisa Chen | 2024-04-11 | 2024-05-05 | Not Started | Medium | Develop wireframes and user flows based on requirements.
Development Sprint 1 | Team A (Dev) | 2024-05-06 | 2024-05-20 | Not Started | High | Implement core features as defined in design.
Quality Assurance Testing | Michael Reed | 2024-05-21 | 2024-06-10 | Not Started | High | Conduct unit, integration, and system testing.
Client Review & Approval | Project Manager | 2024-06-11 | 2024-06-15 | Not Started | High | Final review with client to confirm deliverables.
Go-Live & Training | Team B (Support) | 2024-06-16 | 2024-06-25 | Not Started | Medium | Deploy solution and conduct user training sessions.