## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Notes
Project Kickoff Meeting | Sarah Johnson | 2024-04-05 | Completed | High | 100% | All team members aligned on goals.
Define Project Scope | Michael Chen | 2024-04-10 | In Progress | High | 75% | Review with stakeholders scheduled for Thursday.
Design Wireframes | Lena Rodriguez | 2024-04-18 | Not Started | Medium | 0% | Waiting for scope approval.
Develop MVP Features | David Kim | 2024-05-05 | Blocked | High | 30% | Waiting on API integration from backend team.
User Testing Phase | Sophie Taylor | 2024-05-20 | Not Started | Medium | 0% | To be scheduled after wireframes approval.
Final Review & Launch | Team Lead | 2024-06-01 | Not Started | High | 0% | Final approvals and go-live planning.