## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies
Define project scope and objectives | Sarah Johnson | 2024-03-15 | In Progress | High | None
Identify key stakeholders | Michael Chen | 2024-03-20 | Not Started | Medium | Define project scope
Develop project timeline and milestones | Lena Rodriguez | 2024-03-25 | Not Started | High | Identify key stakeholders
Conduct team kickoff meeting | Team Lead | 2024-03-30 | Not Started | Medium | Project scope finalized
Finalize project budget and resources | David Kim | 2024-04-05 | In Progress | High | Timeline developed