## Worksheet
Task | Owner | Due Date | Status | Priority | Notes/Dependencies
Define project scope and objectives | John Smith | 2024-04-01 | Completed | High | Aligned with stakeholder requirements; approved by leadership.
Form team and assign roles | Alice Johnson | 2024-04-10 | In Progress | Medium | Waiting for final approval of team structure.
Develop project timeline and milestones | Bob Lee | 2024-04-15 | Pending | High | Depends on scope finalization and budget review.
Conduct risk assessment and mitigation planning | Sarah Kim | 2024-04-20 | Not Started | High | Includes technical, timeline, and resource risks.
Organize first team collaboration meeting | James Wong | 2024-04-05 | Completed | Medium | All team members attended; action items documented.
Team Collaboration Project Plan – Editable Version