## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Resources Required | Risk Assessment | Notes
Project Kickoff Meeting | Project Manager | 2024-03-15 | 2024-03-15 | Completed | None | Facilitator, Meeting Room, Equipment | Low | All stakeholders aligned on goals.
Requirements Gathering | Business Analyst | 2024-03-16 | 2024-03-31 | In Progress | Kickoff Meeting | Stakeholders, Interviews, Surveys | Medium | Needs approval from key departments.
Team Onboarding & Training | HR Coordinator | 2024-04-01 | 2024-04-10 | Planned | Requirements Gathering Complete | Training Modules, Guides, Instructors | Low | Ensure all team members are up to speed.
Design Phase Workshop | UX Designer | 2024-04-15 | 2024-04-25 | Pending Approval | Requirements Finalized | Design Tools, Feedback Sessions | Medium | Need stakeholder review before finalizing.
Development Sprint 1 | Lead Developer | 2024-05-01 | 2024-05-15 | Not Started | Design Phase Complete | Code Repository, Testing Tools | High (Integration issues) | Requires clear design handoff.