## Worksheet
Task | Owner | Start Date | End Date | Status | Notes
Define Project Scope | Alice Johnson | 2024-04-01 | 2024-04-15 | In Progress | Gather team input and finalize deliverables.
Team Kickoff Meeting | Bob Smith | 2024-04-16 | 2024-04-16 | Completed | All team members attended and aligned on goals.
Create Collaboration Workflow | Charlie Lee | 2024-04-17 | 2024-05-01 | Pending | Draft document to be reviewed by team.
Weekly Progress Review | Team Lead | 2024-04-23 | 2024-04-23 | Scheduled | Hold at 10 AM every Wednesday.
Finalize Team Roles | Diana Brown | 2024-05-05 | 2024-05-10 | Not Started | Assign responsibilities based on skill sets.