## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
Project Kickoff Meeting | Sarah Chen | 2024-03-01 | 2024-03-03 | Completed | High | None | Finalize project charter and team roles.
Market Research Phase | James Reed | 2024-03-04 | 2024-03-18 | In Progress | High | Kickoff Meeting | Gather customer feedback and competitive analysis.
Design Sprint | Lena Torres | 2024-03-19 | 2024-03-26 | Planned | High | Market Research Phase | Develop wireframes and user journey maps.
Development Phase (Phase 1) | Michael Park | 2024-03-27 | 2024-04-15 | Not Started | Critical | Design Sprint | Build core functionality and APIs.
QA & Testing | Anna Lee | 2024-04-16 | 2024-04-30 | Not Started | High | Development Phase (Phase 1) | Conduct unit, integration, and user acceptance testing.
Project Review & Launch | Sarah Chen | 2024-05-01 | 2024-05-03 | Planned | Medium | QA & Testing | Final review and public launch of the product.