## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Team Notes
Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | Completed | High | 100% | All team members aligned on goals and timelines.
Requirement Gathering | David Lee | 2024-04-15 | In Progress | High | 60% | Stakeholder feedback received; draft documents shared with team.
Design Phase | Anna Patel | 2024-05-10 | Not Started | Medium | 0% | Wireframes and UI mockups to be reviewed in next sprint.
Development Sprint 1 | Team A | 2024-05-25 | Not Started | High | 0% | Frontend and backend modules to be developed in parallel.
QA Testing | James Wilson | 2024-06-15 | Not Started | Medium | 0% | Test cases to be finalized after development completion.
Project Review & Delivery | Sarah Johnson | 2024-07-01 | Not Started | High | 0% | Final sign-off and client presentation scheduled.