## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Meeting Notes
Project Kickoff & Team Alignment | Jane Smith | 2024-04-01 | 2024-04-05 | Completed | 100% | - | Team goals, roles, communication protocols established.
Requirement Gathering Workshop | Mark Johnson | 2024-04-08 | 2024-04-12 | In Progress | 65% | Kickoff meeting | Stakeholders provided inputs; final documentation due 04/15.
Design Phase Planning | Lisa Chen | 2024-04-15 | 2024-04-25 | Not Started | 0% | Requirement Gathering Workshop | Waiting for final requirements to finalize design scope.
Weekly Team Standup Meetings | Team Lead | 2024-04-01 | Ongoing | Ongoing | 85% | - | Daily 10-minute check-ins; progress shared and blockers addressed.
Risk Assessment & Mitigation Plan | Alex Brown | 2024-04-20 | 2024-04-27 | Not Started | 0% | Design Phase Planning | Identifying risks and creating mitigation strategies.