## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Team Members | Notes
Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | 2024-04-01 | Completed | High | Sarah, Mark, Lisa | Finalize project scope and objectives.
Requirements Gathering | Mark Thompson | 2024-04-02 | 2024-04-15 | In Progress | High | Mark, Lisa, Alex | Collect input from stakeholders and document requirements.
Design Phase | Lisa Chen | 2024-04-16 | 2024-05-10 | Planned | Medium | Lisa, Tom, Jane | Develop wireframes and user interface mockups.
Development Phase | Tom Rivera | 2024-05-11 | 2024-07-31 | Not Started | High | Tom, Alex, Jordan | Implement core features based on design.
Testing & QA | Jane Wu | 2024-08-01 | 2024-08-15 | Planned | Medium | Jane, Jordan, Mark | Conduct functional and user acceptance testing.
Deployment & Launch | Sarah Johnson | 2024-08-16 | 2024-08-16 | Not Started | High | Sarah, Tom, Jane | Go live with stakeholders and monitor performance.