## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies
Define Project Scope | Alex Johnson | 01/05/2024 | 01/15/2024 | In Progress | High | None
Stakeholder Interviews | Sara Lee | 01/16/2024 | 01/30/2024 | On Track | Medium | Define Project Scope
Develop Project Plan | Marcus Chen | 02/01/2024 | 02/14/2024 | Not Started | High | Stakeholder Interviews
Team Workshops & Alignment | Lena Martinez | 02/15/2024 | 03/01/2024 | Planned | Medium | Develop Project Plan
Risk Assessment & Mitigation | Ryan Patel | 03/02/2024 | 03/15/2024 | Not Started | High | Team Workshops & Alignment
Final Review & Approval | Project Manager | 04/01/2024 | 04/15/2024 | Not Started | Critical | Risk Assessment & Mitigation