## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Notes
Define Project Scope | Alex Morgan | 2024-03-15 | 2024-03-20 | In Progress | - | Finalize stakeholder requirements.
Create Project Timeline | Sam Rivera | 2024-03-21 | 2024-03-25 | Not Started | Define Scope Task | Include key milestones and deliverables.
Team Kickoff Meeting | Jordan Lee | 2024-03-26 | 2024-03-26 | Scheduled | - | Align team on goals and responsibilities.
Develop Project Budget | Mia Chen | 2024-03-27 | 2024-04-01 | Not Started | Timeline Task | Break down costs by phase and resource.
Review & Approve Plan | Project Manager | 2024-04-02 | 2024-04-03 | Pending | Scope, Timeline, Budget | Final approval before execution.