## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies
Define Project Scope | Sarah Johnson | 2024-03-15 | 2024-03-20 | In Progress | High | -
Conduct Stakeholder Interviews | Michael Chen | 2024-03-21 | 2024-03-28 | Not Started | High | Define Project Scope
Develop Project Timeline | Lisa Rodriguez | 2024-03-29 | 2024-04-05 | Not Started | Medium | Stakeholder Interviews
Design Project Roadmap | David Kim | 2024-04-06 | 2024-04-12 | In Progress | Medium | Project Timeline
Review and Approve Plan | Project Steering Committee | 2024-04-13 | 2024-04-15 | Not Started | High | Design Project Roadmap