## Worksheet
Project Phase | Team Members | Key Activities | Milestones | Due Dates | Status | Owner
Q1 Planning | Project Manager, Product Lead, UX Designer | Define scope, finalize requirements, stakeholder alignment | Finalize project charter | 2024-03-31 | On Track | Anna Johnson
Q1 Design Sprint | UX Designer, UI Developer, Product Lead | Create wireframes, prototype user flows | Prototype reviewed & approved | 2024-04-15 | In Progress | Marcus Lee
Q2 Development | Frontend Dev, Backend Dev, QA Engineer | Build core features, integrate APIs | Feature complete (v1.0) | 2024-06-30 | Not Started | Sarah Kim
Q2 Testing & Review | QA Engineer, Product Lead, UX Designer | Conduct usability testing, bug resolution | All critical bugs fixed | 2024-07-15 | Planned | David Chen
Q3 Launch Preparation | Marketing Lead, DevOps, Project Manager | Finalize go-live plan, training materials | Landing page & campaign ready | 2024-08-31 | Not Started | Anna Johnson
Q4 Post-Launch Review | Project Manager, Customer Support, Analytics Lead | Collect feedback, analyze KPIs | Final report submitted | 2024-10-31 | Not Started | Marcus Lee