## Worksheet
Task | Owner | Start Date | End Date | Status | Progress % | Dependencies
Project Kickoff Meeting | Sarah Johnson | 2023-10-01 | 2023-10-03 | Completed | 100% | None
Requirements Gathering | Mike Chen | 2023-10-04 | 2023-10-15 | In Progress | 65% | Kickoff Meeting
Design Phase | Lisa Wong | 2023-10-16 | 2023-10-25 | Not Started | 0% | Requirements Gathering
Development Phase | Team A | 2023-10-26 | 2023-11-15 | Not Started | 0% | Design Phase
Testing & QA | David Kim | 2023-11-16 | 2023-11-30 | Not Started | 0% | Development Phase
Deployment & Go-Live | All Team Members | 2023-12-01 | 2023-12-05 | Not Started | 0% | Testing & QA