## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Team Collaboration Notes
Project Initiation & Scope Definition | Alice Johnson | 2024-03-01 | 2024-03-15 | In Progress | - | Daily stand-ups with stakeholders to finalize scope.
Team Formation & Roles Assignment | Bob Smith | 2024-03-16 | 2024-03-25 | Not Started | Project Initiation & Scope Definition | Collaborative meeting to assign roles and responsibilities.
Requirement Gathering Workshops | Carol Lee | 2024-03-26 | 2024-04-10 | Planned | Team Formation & Roles Assignment | Facilitated sessions with department leads to capture requirements.
Design Phase - UI/UX Prototypes | David Brown | 2024-04-11 | 2024-05-05 | Not Started | Requirement Gathering Workshops | Collaborative design sprints with UX and development teams.
Development Kickoff & Sprint Planning | Eva Martinez | 2024-05-06 | 2024-07-31 | Not Started | Design Phase - UI/UX Prototypes | Team alignment on sprint goals, tech stack, and deliverables.