## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Project Kickoff Meeting | Jane Doe | 2024-03-15 | 2024-03-15 | Completed | 100% | - | All team members confirmed.
Requirements Gathering | John Smith | 2024-03-16 | 2024-03-28 | In Progress | 65% | Kickoff Meeting | Finalizing user stories.
Design Phase | Lisa Chen | 2024-03-29 | 2024-04-10 | Not Started | 0% | Requirements Finalized | Wireframes and UI mockups.
Development Phase | Team A | 2024-04-11 | 2024-05-30 | Not Started | 0% | Design Phase Complete | Frontend and backend implementation.
Testing & QA | Mike Brown | 2024-06-01 | 2024-06-15 | Not Started | 0% | Development Complete | Unit, integration, and user acceptance testing.
Deployment | Sarah Lee | 2024-06-16 | 2024-06-16 | Not Started | 0% | QA Passed | Live production rollout.