## Worksheet
Week | Team Member | Assigned Task | Due Date | Status | Notes/Comments
1 | John Smith | Finalize project scope document | 2023-10-15 | In Progress | Needs input from stakeholders.
1 | Alice Johnson | Prepare weekly meeting agenda | 2023-10-12 | Completed | Shared with team via email.
2 | Michael Brown | Develop user flow diagrams | 2023-10-22 | Pending | Waiting on UX feedback.
2 | Sarah Lee | Set up project communication channels | 2023-10-18 | Completed | Slack and Teams configured.
3 | David Kim | Conduct technical feasibility review | 2023-10-29 | In Progress | Reviewing system integrations.
3 | Lisa Wong | Update risk assessment matrix | 2023-10-26 | Completed | Added new vendor risks.