## Worksheet
Task | Owner | Deadline | Status | Collaborators | Notes
Project Kickoff Meeting | Sarah Johnson | 2023-10-05 | Completed | Alex Chen, Mark Taylor | Set goals, assign roles, confirm timelines.
Requirements Gathering | Lisa Wong | 2023-10-15 | In Progress | David Kim, Elena Ruiz | Collect stakeholder inputs and validate scope.
Design Phase Review | James Reed | 2023-11-01 | Planned | Sophia Lee, Tom Park | Review wireframes and UI flow with stakeholders.
Development Start | Michael Brown | 2023-11-05 | Not Started | Rachel Smith, Nate Adams | Begin coding and setup environment.