## Worksheet
Task | Owner | Due Date | Status | Collaborators | Notes
Define project goals and scope | Alex Johnson | 2024-03-15 | Completed | Sara Lee, David Kim | Approved by stakeholders. Finalized deliverables list.
Create project timeline and milestones | Maria Lopez | 2024-03-25 | In Progress | James Reed, Emma Watson | Milestones adjusted for client feedback.
Conduct team kickoff meeting | Sam Carter | 2024-03-10 | Completed | All team members present | Agenda and minutes shared via Teams.
Set up collaboration tools (Slack, Trello) | Lisa Chen | 2024-03-18 | Completed | Daniel Brown, Nina Patel | Access granted and onboarding completed.
Review project risks and mitigation plans | Raj Patel | 2024-04-05 | Pending | Sophia Moore, Tom Hughes | Initial risk assessment drafted. Review scheduled.