## Worksheet
Task | Assigned To | Due Date | Status | Progress (%) | Comments
Project Kickoff Meeting | Jane Smith | 2023-10-05 | Completed | 100 | All stakeholders aligned on objectives.
Requirement Gathering | John Doe | <+23-10-15In Progress | 65 | Finalizing user stories from stakeholders.
Design Phase Final Review | Emily Chen | 2023-10-25 | Pending | 0 | Waiting for approval from Product Manager.
Development Sprint 1 | Michael Lee, Sarah Kim | 2023-11-05 | In Progress | 40 | Frontend components completed; backend integration ongoing.
Quality Assurance Testing | Linda Wong | 2023-11-20 | Not Started | 0 | Scheduled after development completion.