## Worksheet
Task | Owner | Deadline | Status | Collaborators | Notes
Project Kickoff Meeting | Alex Johnson | 2024-03-15 | Completed | Samantha Lee, Taylor Reed | Agreed on scope, timeline, and roles.
Requirement Gathering | Samantha Lee | 2024-03-25 | In Progress | Taylor Reed, Jordan Kim | Stakeholder interviews scheduled for next week.
Design Phase Finalization | Taylor Reed | 2024-04-10 | Planned | Jordan Kim, Alex Johnson | Wireframes approved by product lead.
Development Sprint 1 | Jordan Kim | 2024-04-20 | Not Started | Alex Johnson, Samantha Lee | Agile sprint planning in progress.
QA & Testing Cycle | Alex Johnson | 2024-05-05 | Not Started | Taylor Reed, Jordan Kim | Test cases to be drafted by end of April.