## Worksheet
Task | Owner | Due Date | Status | Priority | Collaboration Notes
Define Project Vision & Goals | Alex Thompson | 2024-03-15 | In Progress | High | Align cross-functional teams on mission and KPIs.
Develop Project Timeline & Milestones | Samira Lee | 2024-03-20 | On Track | Medium | Coordinate with Product and Engineering teams.
Conduct Stakeholder Workshops | Jordan Patel | 2024-03-25 | Pending | High | Involve Sales, Marketing, and Legal in requirements gathering.
Set Up Communication Channels | Morgan Clark | 2024-03-18 | Completed | Low | Established weekly syncs and Slack channels.
Finalize Team Roles & Responsibilities | Taylor Reed | 2024-03-28 | In Progress | High | Ensure clarity and accountability across all team members.
Review & Approve Project Charter | Director of Operations | 2024-03-30 | Pending | High | Final sign-off required before kickoff.