## Worksheet
Page | Section | Activity | Responsibility | Deadline | Status
1 | Project Overview | Define team goals and scope | Project Manager | 2024-03-15 | In Progress
2 | Team Roles & Responsibilities | Assign clear roles and accountabilities | HR & Project Lead | 2024-03-10 | Completed
3 | Work Breakdown Structure (WBS) | Create detailed task hierarchy | Project Coordinator | 2024-04-01 | Pending
4 | Communication Plan | Establish meeting schedules and reporting formatsTeam Lead & Communications Officer | 2024-03-20 | In Progress
5 | Risk Assessment & Mitigation | Identify risks and propose solutions | Risk Manager | 2024-03-28 | Pending
6 | Collaboration Tools & Setup | Configure shared platforms (e.g., Teams, Slack, Trello) | IT Support & Operations Lead | 2024-03-18 | Completed
7 | Weekly Retrospective Process | Implement feedback and improvement cycles | All Team Members | 2024-04-05 | Pending
Team Collaboration Project Template – Multi-Page Version