## Worksheet
Task | Owner | Deadline | Status | Priority | Team Input
Define Product Vision | Anna Lee | 2024-03-15 | In Progress | High | Feedback from investors and early users.
Develop MVP Features | Marcus Chen | 2024-04-30 | Not Started | High | Weekly sprint planning with design team.
Onboard New Team Members | Sophia Kim | 2024-03-20 | Completed | Moderate | Role alignment and tool setup.
Conduct User Testing | Liam Reed | 2024-04-15 | Planned | High | Cross-functional review with product and UX.
Prepare Go-to-Market Plan | Olivia Tran | 2024-05-10 | Not Started | High | Collaboration with sales and marketing.