## Worksheet
Task | Owner | Status | Due Date | Progress (%) | Collaboration Notes
Project Kickoff Meeting | Alex Johnson | Completed | 2023-10-01 | 100% | All team members attended and aligned on goals.
Requirement Gathering | Sara Lee | In Progress | 2023-10-15 | 65% | Feedback from stakeholders collected; final review scheduled.
Design Phase | Mike Chen | Planned | 2023-11-01 | 0% | Wireframes and UI mockups to be developed in collaboration with UX team.
Development Sprint 1 | Team A | Not Started | 2023-11-15 | 0% | Team will use daily standups and Jira for real-time collaboration.
Testing & QA | Lena Patel | Scheduled | 2023-12-05 | 20% | Initial test cases created; team will review with product lead.