## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%) | Meeting Notes
Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | 2024-04-01 | Completed | - | 100% | Confirmed team roles, goals, and timeline.
Requirements Gathering | David Lee | 2024-04-02 | 2024-04-15 | In Progress | Kickoff Meeting | 60% | Stakeholder feedback collected; draft document under review.
Design Phase | Lisa Chen | 2024-04-16 | 2024-05-10 | Not Started | Requirements Finalized | 0% | Initial wireframes planned for review in Week 3.
Development Sprint 1 | Team A | 2024-05-11 | 2024-06-05 | Planned | Design Phase Complete | 0% | Frontend components in progress; sprint planning underway.
Testing & QA | Michael Park | 2024-06-06 | 2024-07-15 | Not Started | Development Sprint 1 Complete | 0% | Test cases to be created after development phase.
Deployment & Go-Live | Rachel Kim | 2024-07-16 | 2024-07-18 | Not Started | Testing & QA Complete | 0% | Final review and production deployment scheduled.