## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%)
Project Kickoff Meeting | Sarah Johnson | 2024-03-15 | 2024-03-15 | Completed | - | 100
Requirements Gathering | Mike Chen | 2024-03-16 | 2024-03-25 | In Progress | Kickoff Meeting | 75
Design Phase Finalization | Lena Patel | 2024-03-26 | 2024-04-05 | Not Started | Requirements Gathering | 0
Development Sprint 1 | Team A | 2024-04-06 | 2024-04-15 | Scheduled | Design Phase Finalization | 0
Testing & QA Review | Raj Singh | 2024-04-16 | 2024-04-30 | Not Started | Development Sprint 1 | 0
Go-Live Deployment | Admin Team | 2024-05-01 | 2024-05-01 | Planned | Testing & QA Review | 0