## Worksheet
Month | Team Objective | Key Activities | Responsible Team Members | Milestone Status | Risk & Dependencies
January | Project Kickoff & Strategy Alignment | Define goals, scope, and timelines; conduct stakeholder meetings | Project Manager, Lead Designer, Product Owner | Completed | Stakeholder buy-in required; initial budget approval pending
February | Market Research & User Needs Analysis | Conduct surveys, interviews, and competitive analysis | Research Team, UX Analysts | In Progress | Data collection delays possible; need access to target user groups
March | Product Requirements Finalization | Finalize feature list, prioritize backlog, draft specifications | Product Owner, Engineering Lead | Planned | Feedback loop with design and business units required
April | UI/UX Design & Prototyping | Create wireframes, high-fidelity mockups, and interactive prototypes | Design Team, UX Director | In Progress | Design review sessions scheduled; feedback from stakeholders needed
May | Engineering Development & Sprints | Begin development in agile sprints; complete core functionality | Development Team, QA Lead | Planned | Integration testing to start in June; dependency on design finalization
June | Alpha Testing & Feedback Loop | Conduct internal testing, gather user feedback, iterate improvements | QA Team, Product Owner, UX Team | Scheduled | Testing delays possible due to external dependencies
July | Final Product Review & Approval | Present final deliverables to stakeholders for sign-off | Project Manager, CTO, CFO | Planned | Funding approval may be delayed; marketing alignment required
August | Launch Preparation & Training | Finalize go-live plan, train support staff, prepare documentation | Operations Team, Training Lead | In Progress | Go-live date dependent on final sign-off and vendor readiness
September | Soft Launch & Market Rollout | Launch to select regions; monitor performance and user feedback | Marketing, Sales, Product Team | Scheduled | Need early adoption strategy; track KPIs post-launch
October | Performance Review & Optimization | Analyze usage data, identify bottlenecks, improve user experience | Analytics Team, Engineering | Planned | Integration with new CRM systems pending approval
November | Expansion Planning & Roadmap Update | Explore new features, assess market trends, draft Q4 plan | Product Strategy Team, Marketing | Planned | Need input from customer success team on feature demand
December | Annual Review & Team Reflection | Evaluate project outcomes, celebrate successes, document lessons learned | Full Team, HR Representative | Completed | Report to executive leadership required; future planning session scheduled for January