## Worksheet
Task | Owner | Start Date | End Date | Status | Notes
Project Kickoff Meeting | Alex Johnson | 2024-04-01 | 2024-04-01 | Completed | All team members confirmed attendance.
Requirements Gathering | Sarah Chen | 2024-04-02 | 2024-04-10 | In Progress | Client interviews scheduled for Week 2.
Design Phase | Michael Ross | 2024-04-11 | 2024-04-25 | Not Started | Wireframes and UX mockups to be reviewed.
Development Start | Team A | 2024-04-26 | 2024-05-31 | Not Started | Frontend and backend setup.
Testing & QA | Lisa Park | 2024-06-01 | 2024-06-15 | Not Started | Bug tracking and performance tests.
Final Review & Deployment | Project Manager | 2024-06-16 | 2024-06-18 | Not Started | Approval and go-live process.