## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Notes
Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | - | Finalize team roles and project goals.
Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-31 | In Progress | Kickoff Meeting | Engage stakeholders to collect detailed requirements.
Design Phase | Michael Chen | 2024-04-01 | 2024-04-15 | Planned | Requirements Gathering | Develop wireframes and user interface mockups.
Development Phase | Team A | 2024-04-16 | 2024-05-31 | Not Started | Design Phase | Code implementation based on approved designs.
Testing & QA | Lisa Wang | 2024-06-01 | 2024-06-15 | Not Started | Development Phase | Conduct unit, integration, and user acceptance testing.
Project Review & Launch | John Smith | 2024-06-16 | 2024-06-18 | Not Started | Testing & QA | Final review, training sessions, and go-live.