## Worksheet
Task | Start Date | End Date | Owner | Status | Progress (%)
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | Sarah Johnson | Completed | 100%
Requirements Gathering | 2024-03-16 | 2024-03-28 | Michael Chen | In Progress | 65%
Design Phase | 2024-03-30 | 2024-04-10 | Lena Torres | Not Started | 0%
Development Phase | 2024-04-11 | 2024-05-31 | David Kim | Not Started | 0%
Testing & QA | 2024-06-01 | 2024-06-30 | Emily Patel | Not Started | 0%
Client Review & Sign-off | 2024-07-01 | 2024-07-15 | Client Representative | Not Started | 0%