## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%)
Project Kickoff Meeting | John Smith | 2024-03-01 | 2024-03-01 | Completed | 100
Requirements Gathering | Sarah Lee | 2024-03-02 | 2024-03-15 | In Progress | 65
Design Phase | Mike Chen | 2024-03-16 | 2024-03-31 | Not Started | 0
Development Phase | Lena Torres | 2024-04-01 | 2024-05-15 | Not Started | 0
Testing & QA | David Kim | 2024-05-16 | 2024-06-10 | Not Started | 0
Deployment & Launch | Rachel Green | 2024-06-11 | 2024-06-15 | Not Started | 0