## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies
Project Kickoff Meeting | Sarah Chen | 2024-03-01 | 2024-03-05 | Completed | 100% | None
Requirements Gathering | James Reed | 2024-03-06 | 2024-03-15 | In Progress | 65% | Kickoff Meeting
UI/UX Design Phase | Lena Torres | 2024-03-16 | 2024-04-10 | Planned | 0% | Requirements Gathering
Development Sprint 1 | Team A | 2024-04-11 | 2024-05-05 | Not Started | 0% | UI/UX Design Phase
Testing & QA | David Kim | 2024-05-06 | 2024-05-31 | Scheduled | 0% | Development Sprint 1
Project Review & Launch | Project Manager | 2024-06-01 | 2024-06-15 | Not Started | 0% | Testing & QA