## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Kickoff Meeting | Alex Johnson | 2024-03-01 | 2024-03-01 | Completed | -
Requirements Gathering | Samantha Lee | 2024-03-02 | 2024-03-15 | In Progress | Project Kickoff Meeting
UI/UX Design Phase | Jordan Park | 2024-03-16 | 2024-04-10 | Planned | Requirements Gathering
Development Phase (Frontend) | Mike Thompson | 2024-04-11 | 2024-05-30 | Not Started | UI/UX Design Phase
Development Phase (Backend) | Linda Chen | 2024-05-01 | 2024-06-15 | Not Started | Frontend Development Phase
Testing & QA Review | Raj Patel | 2024-06-16 | 2024-07-10 | Not Started | Backend Development Phase
Deployment & Launch | Taylor Reed | 2024-07-11 | 2024-07-15 | Not Started | Testing & QA Review