## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Milestones | Resources Required | Risk Level | Notes
Project Kickoff Meeting | Project Manager | 2024-03-01 | 2024-03-01 | Completed | None | Meeting Agenda Approved | Facilitator, Minutes Taker | Low | All stakeholders present and aligned.
Requirements Gathering | Business Analyst | 2024-03-02 | 2024-03-15 | In Progress | Kickoff Meeting | Requirement Finalization | Stakeholders, Users, IT Team | Medium | Schedule includes 3 stakeholder workshops.
Design Phase (UI/UX) | UX Designer | 2024-03-16 | 2024-04-10 | Planned | Requirements Finalized | Wireframes Approved | Design Team, Product Owner | Low | Focus on accessibility and usability.
Development Phase | Development Lead | 2024-04-11 | 2024-06-30 | Not Started | Design Phase Complete | Alpha Release Review | Full Engineering Team, QA Lead | High | Critical path; includes integration testing.
QA Testing & Bug Fixes | QA Manager | 2024-07-01 | 2024-07-31 | Not Started | Development Complete | Bug Fix Review Meeting | QA Team, Developers | Medium | Test coverage target: 95%.
User Training & Onboarding | Training Specialist | 2024-08-01 | 2024-08-15 | Not Started | System Go-Live | Training Completion Survey | HR, Department Leads | Low | Online and in-person sessions available.
Project Go-Live & Support | Operations Lead | 2024-08-16 | 2024-09-30 | Not Started | Training Complete | Go-Live Checklist Signed Off | Support Team, IT, Helpdesk | High | Post-launch monitoring and escalation plan in place.