## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies
Project Kickoff Meeting | Alex Johnson | 2024-04-01 | 2024-04-03 | Completed | 100%
Requirements Gathering | Samantha Lee | 2024-04-04 | 2024-04-15 | In Progress | 65% | Kickoff Meeting
Design Phase | Jordan Taylor | 2024-04-16 | 2024-05-05 | Not Started | 0% | Requirements Gathering
Development Sprint 1 | Team A | 2024-05-06 | 2024-05-20 | Planned | 0% | Design Phase
Testing & QA | Morgan White | 2024-05-21 | 2024-06-10 | Not Started | 0% | Development Sprint 1
Final Review & Deployment | All Team | 2024-06-11 | 2024-06-15 | Not Started | 0% | Testing & QA