## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Project Kickoff Meeting | Jane Doe | 2024-03-01 | 2024-03-01 | Completed | 100% | All team members attended and agreed on scope.
Market Research Phase | John Smith | 2024-03-04 | 2024-03-15 | In Progress | 65% | Survey data collected; analysis pending.
Design Finalization | Lisa Chen | 2024-03-16 | 2024-04-05 | Not Started | 0% | Wireframes approved; design team to begin.
Development Phase | Mike Turner | 2024-04-06 | 2024-05-31 | Not Started | 0% | Frontend and backend development to begin.
Testing & QA | Sarah Kim | 2024-06-01 | 2024-06-30 | Not Started | 0% | Beta testing to be scheduled post-development.
Launch & Feedback | Team Lead | 2024-07-01 | 2024-07-15 | Not Started | 0% | Public launch planned with post-launch survey.