## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Milestones | Team Input | Risk Level
Project Kickoff Meeting | Manager A | 2024-01-15 | 2024-01-16 | 2 | Completed | - | Kickoff Complete | All team members attended | Low
Requirements Gathering | Analyst B | 2024-01-17 | 2024-01-31 | 15 | In Progress | Kickoff Meeting | Final Requirements Signed | Input from Product & UX teams | Medium
Design Phase | Designer C | 2024-02-01 | 2024-02-15 | 15 | Planned | Requirements Finalized | Design Review Approved | Collaboration with Developers | Low
Development Phase | Dev Team D | 2024-02-16 | 2024-03-31 | 45 | Not Started | Design Approved | Midpoint Review, Final Build | Daily stand-ups with QA | High
Testing & Quality Assurance | QA Lead E | 2024-04-01 | 2024-04-15 | 15 | Planned | Development Complete | Bug Fix Review, Final Test Passed | Team input on issue tracking | Medium
Deployment & Launch | Ops Manager F | 2024-04-16 | 2024-04-18 | 3 | Scheduled | Testing Complete | Go-Live Confirmed | All teams present for handover | Low